## Sheet
Control No | Part name | Part No | Mold No | Cavity | Factory | Type | Product type | 1st ship plan | Mold receive plan | Mold receive actual | Product info | Feasibility | Preparation | Try Injection | Try Assy | Try Packing | Try Confirmation | Mass production | Follow up
C-APQP-001 | HS226+64FUA-NA |  | V557-1 | CV1-CV8 | F1 | APQP | Unit | 2025-11-30 | 2024-08-30 |  | Processing-10/Jun | Finish | Finish | IM, MM, PC, PV, QA-14/Aug | NA | PK, PV, PC-14/Aug | Wait-14-Aug | Wait-16-Dec | Processing
C-APQP-002 | HS226+64FUB-LGR | 6099-0691 | V557-1 | CV1-CV8 | F1 | APQP | Child part | 2025-11-30 | 2024-07-25 |  | Finish | Finish | Finish | IM, MM, PC, PV, QA-30/Aug | NA | PK, PV, PC-30/Aug | Wait-30/Aug | Wait-30/Dec | Processing
C-APQP-003 | HS226+64FL-NA | 6099-0698 | V558-1 | CV1-CV4 | F1 | APQP | Child part | 2025-11-30 | 2024-07-25 |  | Finish | Finish | Finish | IM, MM, PC, PV, QA-14/Aug | NA | PK, PV, PC-14/Aug | Wait-14/Aug | Wait-16/Dec | Processing
C-APQP-004 | 12H41NYH13F-GR | 6099-0852 | V573-1 | CV1-CV2 | F1 | APQP | Child part | 2025-01-01 | 2024-08-01 |  | Finish | Finish | Finish | Finish | NA | NA | Wait | Wait | Processing
C-APQP-005 | CVR8282142460NA | 1 | V584-1 | CV1-CV2 | F1 | APQP | Child part | 2025-01-01 | 2024-09-20 |  | Finish | Finish | Finish | Finish | NA | NA | ASSY, IM, QA | Wait | Processing
C-APQP-006 | 12H41NYM13F-NA | 1 | V572-1 | CV1-CV4 | F1 | APQP | Child part | 2025-01-01 | 2024-07-05 |  | IM-14/Jun | IM, PC, PK, QA-14/Jun | Wait-28/Jun | Wait | NA | NA | Wait | Wait | Processing
C-APQP-008 | 12H66NYO78F-Y | 111 |  | CV1-CV12 | F1 | APQP | Unit | 2025-01-01 | 2024-09-20 |  | PC, PK-20/Jun | IM, PC, PK, QA-20/Jun | Wait-17/Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-009 | 12H72NYO78F-NA |  | V583-1 | CV1-CV12 | F1 | APQP | Unit | 2025-01-01 | 2024-09-20 |  | Finish | Finish | Finish | Finish | NA | Finish | ASSY, IM, QA | Wait | Processing
C-APQP-011 | 33A00NYH19F-NA |  | V580-1 | CV1-CV3 | F1 | APQP | Assy | 2025-01-01 | 2024-07-05 |  | Finish | Finish | Finish | IM, MM, PC, PV, QA | ASSY, PV, QA, PC | PK, PV, PC | Wait | Wait | Processing
C-APQP-013 | HS226+64FUB-DGR | 1 | V557-1 | CV1-CV8 | F1 | APQP | Child part | 2025-11-30 | 2024-07-25 |  | IM-10/Jun | IM, PC, PK, QA-10/Jun | Wait-30/Jul | Wait-14/Aug | NA | NA | Wait-14/Aug | Wait-16/Dec | Processing
C-APQP-014 | HS226+64FUC-B |  | V557-1 | CV1-CV8 | F1 | APQP | Unit | 2025-11-30 | 2024-07-25 |  | Finish | Finish | Finish | Finish | NA | Finish | ASSY, IM, QA | Wait | Processing
C-APQP-015 | HS226+64FUD-L |  | V557-1 | CV1-CV8 | F1 | APQP | Unit | 2025-11-30 | 2024-07-25 |  | IM-12-Jun | Wait-12-Jul | Wait-02-Aug | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-016 | HS226+64FUE-LGR |  | V557-1 | CV1-CV8 | F1 | APQP | Unit | 2025-11-30 | 2024-07-25 |  | IM-12-Jun | Wait-12-Jul | Wait-02-Aug | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-017 | HS226+64FUF-G |  | V557-1 | CV1-CV8 | F1 | APQP | Unit | 2025-11-30 | 2024-07-25 |  | IM-12-Jun | Wait-12-Jul | Wait-02-Aug | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-018 | HS226+64FUG-BR |  | V557-1 | CV1-CV8 | F1 | APQP | Unit | 2025-11-30 | 2024-07-25 |  | IM-12-Jun | Wait-12-Jul | Wait-02-Aug | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-019 | HS226+64FL-LGR |  | V558-1 | CV1-CV4 | F1 | APQP | Unit | 2025-11-30 | 2024-07-25 |  | IM-12-Jun | Wait-12-Jul | Wait-02-Aug | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-020 | HS226+64FL-DGR |  | V558-1 | CV1-CV4 | F1 | APQP | Unit | 2025-11-30 | 2024-07-25 |  | IM-12-Jun | Wait-12-Jul | Wait-02-Aug | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-021 | HS226+64FL-B |  | V558-1 | CV1-CV4 | F1 | APQP | Unit | 2025-11-30 | 2024-07-25 |  | IM-12-Jun | Wait-12-Jul | Wait-02-Aug | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-022 | HS226+64FL-L |  | V558-1 | CV1-CV4 | F1 | APQP | Unit | 2025-11-30 | 2024-07-25 |  | IM-12-Jun | Wait-13-Jul | Wait-02-Aug | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-023 | HS226+64FL-LGR |  | V558-1 | CV1-CV4 | F1 | APQP | Unit | 2025-11-30 | 2024-07-25 |  | IM-12-Jun | Wait-12-Jul | Wait-02-Aug | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-024 | HS226+64FL-G |  | V558-1 | CV1-CV4 | F1 | APQP | Unit | 2025-11-30 | 2024-07-25 |  | IM-12-Jun | Wait-12-Jul | Wait-02-Aug | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-025 | HS226+64FL-BR |  | V558-1 | CV1-CV4 | F1 | APQP | Unit | 2025-11-30 | 2024-07-25 |  | IM-12-Jun | Wait-12-Jul | Wait-02-Aug | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-026 | 12H41NYS13F-NA | 1111 | V571-1 | CV1-CV4 | F1 | APQP | Child part | 2025-01-01 | 2024-06-28 |  | IM, PK-28/Jun | IM, PC, PK, QA-28/Jun | Wait-30/Jul | Wait | NA | NA | Wait | Wait | Processing
C-APQP-027 | 33A00NYS19F-NA |  | V581-1 | CV1-CV4 | F1 | APQP | Child part | 2025-01-01 | 2024-07-05 |  | IM-13/Jun | Wait-27-Jun | Wait-22-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-028 | 33A00NYM19F-NA |  | V581-1 | CV1-CV4 | F1 | APQP | Child part | 2025-01-01 | 2024-07-05 |  | IM, PC-13/Jun | Wait-27-Jun | Wait-22-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-029 | 12H42NYH24F-B |  | V570-1 | CV1-CV2 | F1 | APQP | Assy | 2025-01-01 | 2024-08-28 |  | IM, PC-12/Jun | Wait-26-Jun | Wait-15-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-030 | 12H42NYM24F-NA |  | V572-1 | CV1-CV4 | F1 | APQP | Child part | 2025-01-01 | 2024-08-28 |  | IM, PC-12/Jun | Wait-26-Jun | Wait-15-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-031 | 12H42NYS24F-NA |  | V571-1 | CV1-CV4 | F1 | APQP | Child part | 2025-01-01 | 2024-08-28 |  | IM, PC-12/Jun | Wait-26-Jun | Wait-15-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-032 | 12H43NFH22F-NA |  | V568-1 | CV1-CV8 | F1 | APQP | Assy | 2025-01-01 | 2024-08-28 |  | IM, PC-12/Jun | Wait-26-Jun | Wait-15-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-033 | 12H43NFS22F-NA |  | V569-1 | CV1-CV8 | F1 | APQP | Child part | 2025-01-01 | 2024-08-28 |  | IM, PC-12/Jun | Wait-26-Jun | Wait-15-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-034 | 12H44NFH22F-GR |  | V568-1 | CV1-CV8 | F1 | APQP | Assy | 2025-01-01 | 2024-08-28 |  | IM, PC-12/Jun | Wait-26-Jun | Wait-15-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-035 | 12H45NFH22F-B |  | V568-1 | CV1-CV8 | F1 | APQP | Assy | 2025-01-01 | 2024-08-28 |  | IM, PC-12/Jun | Wait-26-Jun | Wait-15-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-036 | 12H46NFH26F-B |  | V574-1 | CV1-CV4 | F1 | APQP | Assy | 2025-01-01 | 2024-08-28 |  | IM, PC-12/Jun | Wait-26-Jun | Wait-15-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-037 | 12H46NFS26F-NA |  | V575-1 | CV1-CV4 | F1 | APQP | Child part | 2025-01-01 | 2024-08-28 |  | IM, PC-12/Jun | Wait-26-Jun | Wait-15-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-038 | 12H47NFH26F-NA |  | V574-1 | CV1-CV4 | F1 | APQP | Assy | 2025-01-01 | 2024-08-28 |  | IM, PC-12/Jun | Wait-26-Jun | Wait-15-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-039 | HE020-32FU-LGR |  | V552-1 | CV1-CV4 | F1 | APQP | Unit | 2024-10-01 | 2024-08-05 |  | IM, MM, PC-12/Jun | Wait-26-Jun | Wait-22-Aug | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-040 | HE020-32FL-LGR |  | V553-1 | CV1-CV4 | F1 | APQP | Unit | 2024-10-01 | 2024-08-05 |  | IM, MM, PC-13/Jun | Wait-26-Jun | Wait-28-Aug | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-041 | HE020-32FL-B |  | V553-1 | CV1-CV4 | F1 | APQP | Unit | 2024-10-01 | 2024-08-05 |  | IM, MM, PC-12/Jun | Wait-26-Jun | Wait-26-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-042 | 12H28NYH30F-NA |  | V562-1 | CV1-CV4 | F1 | APQP | Assy | 2025-02-01 | 2024-08-05 |  | PC-12/Jun | Wait-27-Jun | Wait-29-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-043 | 12H28NYS30F-NA | 111 | V564-1 | CV1-CV4 | F1 | APQP | Child part | 2025-02-01 | 2024-08-05 |  | PC-12/Jun | IM, PC, PK, QA-12/Jun | Wait-29/Jul | Wait | NA | NA | Wait | Wait | Processing
C-APQP-044 | 12H24WYH42F-B |  | V554-1 | CV1-CV2 | F1 | APQP | Assy | 2025-02-01 | 2024-07-02 |  | PC-07/Jun | Wait-21-Jun | Wait-22-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-045 | 12H24WYS42F-NA |  | V550-1 | CV1-CV2 | F1 | APQP | Child part | 2025-02-01 | 2024-07-02 |  | PC-07/Jun | Wait-21-Jun | Wait-22-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-046 | 12H24WYO42F-GR |  | V551-1 | CV1-CV2 | F1 | APQP | Child part | 2025-02-01 | 2024-07-02 |  | PC-07/Jun | IM, PC, PK, QA-07/Jun | Wait-22-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-047 | HFDU2-6F-HSG-NA |  | V536-1 | CV1-CV4 | F1 | APQP | Child part |  | 2027-12-25 |  | MM, PC, PK-24/Jun | IM, PC, PK, QA-24/Jun | Wait | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-048 | 12H26WYH08F-B |  | V587-1 | CV1-CV8 | F2 | APQP | Assy | 2024-09-27 | 2024-07-12 |  | MM, PC-13-Jun | Wait-27-Jun | Wait-29-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-049 | 12H26WYS08F-NA |  | V579-1 | CV1-CV8 | F2 | APQP | Child part | 2024-09-27 | 2024-07-12 |  | PC-10-Jun | Wait-24-Jun | Wait-24-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-050 | 12H29NYL30F-B |  | V567-1 | CV1-CV4 | F1 | APQP | Unit | 2025-02-01 | 2024-08-05 |  | PC-10/Jun | Wait-24-Jun | Wait-24-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-051 | 12H31NYH30F-GR |  | V562-1 | CV1-CV4 | F1 | APQP | Assy | 2025-02-01 | 2024-06-25 |  | PC-10/Jun | Wait-24-Jun | Wait-24-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-052 | 12H33NYH34F-NA |  | V561-1 | CV1-CV2 | F1 | APQP | Assy | 2025-02-01 | 2024-06-25 |  | PC-10/Jun | Wait-24-Jun | Wait-24-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-053 | 12H33NYS34F-NA |  | V563-1 | CV1-CV4 | F1 | APQP | Child part | 2025-02-01 | 2024-06-25 |  | PC-10/Jun | Wait-24-Jun | Wait-24-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-054 | 12H34NYL34F-GR |  | V566-1 | CV1-CV2 | F1 | APQP | Unit | 2025-02-01 | 2024-08-05 |  | PC-13/Jun | Wait-27-Jun | Wait-29-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-055 | 12H36NYH27F-NA |  | V560-1 | CV1-CV2 | F1 | APQP | Assy | 2025-02-01 | 2024-06-25 |  | PC-10/Jun | Wait-24-Jun | Wait-24-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-056 | 12H36NYS27F-NA |  | V563-1 | CV1-CV4 | F1 | APQP | Child part | 2025-02-01 | 2024-06-25 |  | PC-10/Jun | Wait-24-Jun | Wait-24-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-057 | 12H37NYL27F-B |  | V565-1 | CV1-CV2 | F1 | APQP | Unit | 2025-02-01 | 2024-08-05 |  | MM, PC-13/Jun | Wait-27-Jun | Wait-29-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-058 | 12H38N3H01F-NA |  | V559-1 | CV1-CV8 | F1 | APQP | Unit | 2025-02-01 | 2024-06-25 |  | PC-10/Jun | Wait-14-Jun | Wait-20-Jun | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-059 | 12H39N3H01F-NA |  | V559-1 | CV1-CV8 | F1 | APQP | Unit | 2025-02-01 | 2024-06-25 |  | PC-10/Jun | Wait-24-Jun | Wait-24-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-060 | 12H40N3H01F-NA |  | V559-1 | CV1-CV8 | F1 | APQP | Unit | 2025-02-01 | 2024-06-25 |  | PC-10/Jun | Wait-24-Jun | Wait-24-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-061 | HFCV-H01M-NA |  | V545-1 | CV1-CV8 | F1 | APQP | Assy | 2024-10-01 | 2024-08-06 |  | IM, PC-10/Thg6 | Wait-24-Jun | Wait-24-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-062 | HFCV-S01-NA |  | V546-1 | CV1-CV16 | F1 | APQP | Child part | 2024-10-01 | 2024-06-05 |  | PC-10/Jun | IM, PC, PK, QA-10/Jun | Wait-24-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-063 | HFCV-H01F-NA |  | V547-1 | CV1-CV16 | F1 | APQP | Assy | 2024-10-01 | 2024-08-06 |  | IM, PC-10/Thg6 | Wait-24-Jun | Wait-25-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-064 | HFCV-H02F-NA |  | V548-1 | CV1-CV2 | F2 | APQP | Assy | 2024-09-01 | 2024-06-28 |  | IM, PC-10-Jun | Wait-24-Jun | Wait-25-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-065 | HFCV-S02-NA |  | V548-1 | CV1-CV2 | F2 | APQP | Child part | 2024-09-01 | 2024-06-28 |  | IM, PC-11-Jun | Wait-25-Jun | Wait-24-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-066 | H/LHSG6+2HYB-M |  | V576-1 | CV1-CV4 | F2 | APQP | Assy | 2024-09-27 | 2024-07-12 |  | MM-12/Jun | Wait-26/Jun | Wait-26/Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-067 | H/LRTN6+2HYB-M |  | V577-1 | CV1-CV8 | F2 | APQP | Child part | 2024-09-27 | 2024-07-12 |  | Finish | PC, QA-26/Jun | Wait-26-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-068 | 12C05WYH46F-B |  | V508-3 | CV5-CV6 | F1 | Add | Assy |  | 2024-06-14 |  | IM, MM, PC, PK-10-Jun | Wait-24-Jun | Wait-24-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-069 | 12E84WQH02F-B |  | V506-2 | CV5-CV12 | F2 | Add | Assy |  | 2024-06-30 |  | IM, MM, PC, PK-10-Jun | Wait-13-Jun | Wait-27-Jun | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-070 | 12790WQH06F-GR |  | V100-8 | CV41-CV56 | F2 | Add | Assy |  | 2024-07-15 |  | IM, MM, PC-13-Jun | Wait-27-Jun | Wait-25-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-071 | 78190NYH63M-NA |  | V451-5 | CV11-CV14 | F1 | Add | Assy |  | 2024-08-30 |  | IM, MM-13/Jun | Wait-27-Jun | Wait-26-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-072 | 12G02WYO42F-B |  | V473-2 | CV3-CV6 | F1 | Add | Child part |  | 2024-08-31 |  | IM, MM-13/Jun | Wait-27-Jun | Wait-26-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-073 | LIF MP100GY-N |  | V394-2 | CV5-CV12 | F2 | Add | Assy |  | 2024-10-10 |  | IM, MM, PC, PK-20-Jun | Wait-10-Jul | Wait-01-Aug | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-074 | 12G02WYH42F-B |  | V471-3 | CV5-CV6 | F1 | Add | Assy |  | 2024-08-31 |  | IM, MM, PC, PK-13-Jun | Wait-27-Jun | Wait-30-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-075 | 12520WQH08F-GR |  | V369-4 | CV13-CV20 | F2 | Add | Assy |  | 2024-09-09 |  | IM, MM, PC, PK-13-Jun | Wait-27-Jun | Wait-30-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-076 | 12E32NFH36F-NA |  | V475-3 | CV9-CV12 | F1 | Add | Assy |  | 2024-09-16 |  | IM, MM-13/Jun | Wait-27-Jun | Wait-30-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-077 | CVR8282130600B |  | V330-3 | CV33-CV48 | F1 | Add | Unit |  | 2024-10-24 |  | Finish | PC, PK, QA-27/Jun | Wait-30-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-078 | 78190NYS63M-NA |  | V452-2 | CV5-CV6 | F1 | Add | Assy |  | 2023-12-14 |  | IM, MM-13/Jun | Wait-27-Jun | Wait-30-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-079 | 78240NYS63F-NA |  | V452-2 | CV5-CV6 | F1 | Add | Assy |  | 2023-12-14 |  | IM, MM-13/Jun | Wait-27-Jun | Wait-29-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-080 | 12F11NFH02M-NA |  | V517-1 | CV1-CV4 | F1 | Expand | Unit |  | 2024-06-14 |  | MM, PC, PK-20/Jun | Wait-11-Jul | Wait-12-Aug | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-081 | 12F12NFH02M-B |  | V517-1 | CV1-CV4 | F1 | Expand | Unit |  | 2024-06-14 |  | MM, PC-13/Jun | Wait-27-Jun | Wait-30-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-082 | 12F13NFH02M-L |  | V517-1 | CV1-CV1 | F1 | Expand | Unit |  | 2024-06-14 |  | MM, PC-13/Jun | Wait-27-Jun | Wait-30-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-084 | FR25-32+6-11FN |  | V503-2 | CV3-CV4 | F1 | Add | Assy |  | 2024-05-17 | 2024-05-16 | IM, MM, PK-14/Jun | Wait-14-Jun | Wait-14-Jun | Wait-14-Jun | Wait-14-Jun | Wait-14-Jun | Wait-14-Jun | Wait-30-Jun | Processing
C-APQP-085 | HSG220+64FUB |  | V555-1 | CV1-CV4 | F1 | APQP | Unit |  | 2024-04-12 | 2024-03-25 | Finish | PC, PK, QA-14/Jun | Wait-14-Jun | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-086 | HSG220+64FLB |  | V556-1 | CV1-CV4 | F1 | APQP | Unit |  | 2024-04-12 | 2024-03-25 | Finish | PC, PK, QA-14/Jun | Wait-14-Jun | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-087 | HSG220+64FUNA |  | V555-1 | CV1-CV4 | F1 | APQP | Unit |  | 2024-04-12 | 2024-03-25 | Finish | PC, PK, QA-14/Jun | Wait-14-Jun | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-088 | HSG220+64FUB2 |  | V555-1 | CV1-CV4 | F1 | APQP | Unit |  | 2024-04-12 | 2024-03-25 | Finish | PC, PK, QA-14/Jun | Wait-14-Jun | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-089 | HSG220+64FLB2 |  | V556-1 | CV1-CV4 | F1 | APQP | Unit |  | 2024-04-12 | 2024-03-25 | Finish | PC, PK, QA-14/Jun | Wait-14-Jun | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-090 | HSG220+64FUNA2 |  | V555-1 | CV1-CV4 | F1 | APQP | Unit |  | 2024-04-12 | 2024-03-25 | Finish | PC, PK, QA-14/Jun | Wait-14-Jun | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-091 | HSG220+64FLNA |  | V556-1 | CV1-CV4 | F1 | APQP | Unit |  | 2024-04-12 | 2024-03-25 | Finish | PC, PK, QA-14/Jun | Wait-14-Jun | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-092 | HSG220+64FLNA2 |  | V556-1 | CV1-CV4 | F1 | APQP | Unit |  | 2024-04-12 | 2024-03-25 | Finish | PC, PK, QA-14/Jun | Wait-14-Jun | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-093 | 12808N6S02F-NA |  | V231-4 | CV25-CV40 | F1 | Add | Assy |  | 2024-02-28 | 2023-12-28 | PK-14/Jun | Wait-14-Jun | Wait-14-Jun | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-094 | 12808N6H02F-B |  | V230-4 | CV33-CV48 | F1 | APQP | Assy |  | 2024-02-28 | 2023-12-28 | Finish | ASSY, PC, PK, QA-14/Jun | Wait-14-Jun | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-095 | 12F38NFH08F-GR |  | V516-1 | CV1-CV4 | F1 | Expand | Unit |  | 2024-02-14 | 2024-02-14 | IM, MM, PC, PK-26-Jun | Wait-28-Jun | Wait-30-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-096 | 1 |  | 1 | 1 | F1 | Add | Child part | 2024-06-01 | 2024-06-01 | 2024-06-01 | QA | IM, PC, PK, QA | Wait | Wait | NA | NA | Wait | Wait | Processing
C-APQP-097 | 2 | 2 | 2 | 2 | F1 | APQP | Assy | 2024-06-02 | 2024-06-02 |  | QA | ASSY, IM, PC, PK, QA | Wait | Wait | Wait | Wait | Wait | Wait | Processing