## Sheet
Control No | Part name | Part No | Mold No | Cavity | Factory | Type | Product type | 1st ship plan | Mold receive plan | Mold receive actual | Product info | Feasibility | Preparation | Try Injection | Try Assy | Try Packing | Try Confirmation | Mass production | Follow up
C-APQP-001 | HS226+64FUA-NA | 6099-0690 | V557-1 | CV1-CV8 | F1 | APQP | Unit | 2025-11-30 | 2024-09-03 |  | Finish | Finish | ASSY, IM, MM, PV, QA-30-Jul | Wait-14-Aug | NA | Wait-14-Aug | Wait-14-Aug | Wait-16-Dec | Processing
C-APQP-002 | HS226+64FUB-LGR | 6099-0691 | V557-1 | CV1-CV8 | F1 | APQP | Unit | 2025-11-30 | 2024-09-03 |  | Finish | Finish | ASSY, IM, MM, PV, QA-15-Jul | Wait-30-Aug | NA | Wait-30-Aug | Wait-30-Aug | Wait-30-Dec | Processing
C-APQP-003 | HS226+64FL-NA | 6099-0698 | V558-1 | CV1-CV4 | F1 | APQP | Unit | 2025-11-30 | 2024-09-03 |  | Finish | Finish | ASSY, IM, MM, PV, QA-15-Jul | Wait-14-Aug | NA | Wait-14-Aug | Wait-14-Aug | Wait-16-Dec | Processing
C-APQP-004 | 12H41NYH13F-GR | 6099-0852 | V573-1 | CV1-CV2 | F1 | APQP | Assy | 2025-01-01 | 2024-08-28 |  | Finish | Finish | ASSY, IM, MM, PV-20-Aug | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-005 | CVR8282142460NA | 69118099 | V584-1 | CV1-CV2 | F1 | APQP | Unit | 2025-01-01 | 2024-08-01 |  | Finish | Finish | ASSY, IM, MM, PV, QA-08-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-006 | 12H41NYM13F-NA | 6099-0853 | V572-1 | CV1-CV4 | F1 | APQP | Child part | 2025-01-01 | 2024-08-28 |  | Finish | Finish | ASSY, IM, MM-05-Jul | Wait | NA | NA | Wait | Wait | Processing
C-APQP-008 | 12H66NYO78F-Y | 6099-0880 | V583-1 | CV1-CV12 | F1 | APQP | Unit | 2025-01-01 | 2024-09-18 |  | Finish | Finish | ASSY, IM, MM, PC, PV, QA-05-Sep | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-009 | 12H72NYO78F-NA | 6099-0891 | V583-1 | CV1-CV12 | F1 | APQP | Unit | 2025-01-01 | 2024-09-18 |  | Finish | Finish | ASSY, IM, MM, PV, QA-05-Sep | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-011 | 33A00NYH19F-NA | 60990860 | V580-1 | CV1-CV3 | F1 | APQP | Assy | 2025-01-01 | 2024-08-05 |  | Finish | Finish | ASSY, IM, MM-05-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-013 | HS226+64FUB-DGR | 6099-0692 | V557-1 | CV1-CV8 | F1 | APQP | Unit | 2025-11-30 | 2024-07-25 |  | Finish | Finish | ASSY, IM, MM, PV, QA-10-Jul | Wait-14-Aug | NA | Wait-14-Aug | Wait-14-Aug | Wait-16-Dec | Processing
C-APQP-014 | HS226+64FUC-B | 6099-0693 | V557-1 | CV1-CV8 | F1 | APQP | Unit | 2025-11-30 | 2024-07-25 |  | Finish | Finish | ASSY, IM, MM, PV, QA-10-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-015 | HS226+64FUD-L | 6099-0694 | V557-1 | CV1-CV8 | F1 | APQP | Unit | 2025-11-30 | 2024-07-25 |  | Finish | Finish | ASSY, IM, MM, QA-05-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-016 | HS226+64FUE-LGR | 6099-0695 | V557-1 | CV1-CV8 | F1 | APQP | Unit | 2025-11-30 | 2024-07-25 |  | Finish | Finish | ASSY, IM, MM, QA-05-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-017 | HS226+64FUF-G | 6099-0696 | V557-1 | CV1-CV8 | F1 | APQP | Unit | 2025-11-30 | 2024-07-25 |  | Finish | Finish | ASSY, IM, MM, PV, QA-05-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-018 | HS226+64FUG-BR | 6099-0697 | V557-1 | CV1-CV8 | F1 | APQP | Unit | 2025-11-30 | 2024-07-25 |  | Finish | Finish | ASSY, IM, MM, PV, QA-05-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-019 | HS226+64FL-LGR | 6099-0699 | V558-1 | CV1-CV4 | F1 | APQP | Unit | 2025-11-30 | 2024-07-25 |  | Finish | Finish | ASSY, IM, MM, PV, QA-05-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-020 | HS226+64FL-DGR | 6099-0700 | V558-1 | CV1-CV4 | F1 | APQP | Unit | 2025-11-30 | 2024-07-25 |  | Finish | Finish | ASSY, IM, MM, PV, QA-05-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-021 | HS226+64FL-B | 6099-0701 | V558-1 | CV1-CV4 | F1 | APQP | Unit | 2025-11-30 | 2024-07-25 |  | Finish | Finish | ASSY, IM, MM, PV, QA-05-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-022 | HS226+64FL-L | 6099-0702 | V558-1 | CV1-CV4 | F1 | APQP | Unit | 2025-11-30 | 2024-07-25 |  | Finish | Finish | ASSY, IM, MM, PV, QA-05-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-023 | HS226+64FL-LGR | 6099-0699 | V558-1 | CV1-CV4 | F1 | APQP | Unit | 2025-11-30 | 2024-07-25 |  | Finish | Finish | ASSY, IM, MM, PV, QA-05-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-024 | HS226+64FL-G | 6099-0703 | V558-1 | CV1-CV4 | F1 | APQP | Unit | 2025-11-30 | 2024-07-25 |  | Finish | Finish | ASSY, IM, MM, PV, QA-05-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-025 | HS226+64FL-BR | 6099-0704 | V558-1 | CV1-CV4 | F1 | APQP | Unit | 2025-11-30 | 2024-07-25 |  | Finish | Finish | ASSY, IM, MM, PV, QA-05-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-026 | 12H41NYS13F-NA | 6099-0854 | V571-1 | CV1-CV4 | F1 | APQP | Child part | 2025-01-01 | 2024-08-28 |  | Finish | PC, PK-04-Jul | Wait-30-Jul | Wait | NA | NA | Wait | Wait | Processing
C-APQP-027 | 33A00NYS19F-NA | 60990861 | V581-1 | CV1-CV4 | F1 | APQP | Child part | 2025-01-01 | 2024-08-05 |  | Finish | Finish | ASSY, IM, MM-01-Jul | Wait | NA | NA | Wait | Wait | Processing
C-APQP-028 | 33A00NYM19F-NA | 60990862 | V581-1 | CV1-CV4 | F1 | APQP | Child part | 2025-01-01 | 2024-08-05 |  | Finish | Finish | ASSY, IM, MM-01-Jul | Wait | NA | NA | Wait | Wait | Processing
C-APQP-029 | 12H42NYH24F-B | 6099-0848 | V570-1 | CV1-CV2 | F1 | APQP | Assy | 2025-01-01 | 2024-08-28 |  | Finish | Finish | ASSY, IM, MM, PV-15-Aug | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-030 | 12H42NYM24F-NA | 6099-0849 | V572-1 | CV1-CV4 | F1 | APQP | Child part | 2025-01-01 | 2024-08-28 |  | Finish | Finish | ASSY, IM, MM, PV-15-Aug | Wait | NA | NA | Wait | Wait | Processing
C-APQP-031 | 12H42NYS24F-NA | 6099-0850 | V571-1 | CV1-CV4 | F1 | APQP | Child part | 2025-01-01 | 2024-08-28 |  | Finish | Finish | ASSY, IM, MM, PV-15-Aug | Wait | NA | NA | Wait | Wait | Processing
C-APQP-032 | 12H43NFH22F-NA | 6099-0841 | V568-1 | CV1-CV8 | F1 | APQP | Assy | 2025-01-01 | 2024-08-28 |  | Finish | Finish | ASSY, IM, MM, PV-15-Aug | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-033 | 12H43NFS22F-NA | 6099-0842 | V569-1 | CV1-CV8 | F1 | APQP | Child part | 2025-01-01 | 2024-08-28 |  | Finish | Finish | ASSY, IM, MM, PV-15-Aug | Wait | NA | NA | Wait | Wait | Processing
C-APQP-034 | 12H44NFH22F-GR | 6099-0844 | V568-1 | CV1-CV8 | F1 | APQP | Assy | 2025-01-01 | 2024-08-28 |  | Finish | Finish | ASSY, IM, MM, PV-15-Aug | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-035 | 12H45NFH22F-B | 6099-0846 | V568-1 | CV1-CV8 | F1 | APQP | Assy | 2025-01-01 | 2024-08-28 |  | Finish | Finish | ASSY, IM, MM, PV-15-Aug | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-036 | 12H46NFH26F-B | 6099-0859 | V574-1 | CV1-CV4 | F1 | APQP | Assy | 2025-01-01 | 2024-08-28 |  | Finish | Finish | ASSY, IM, MM, PV-15-Aug | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-037 | 12H46NFS26F-NA | 6099-0857 | V575-1 | CV1-CV4 | F1 | APQP | Child part | 2025-01-01 | 2024-08-28 |  | Finish | Finish | ASSY, IM, MM, PV-15-Aug | Wait | NA | NA | Wait | Wait | Processing
C-APQP-038 | 12H47NFH26F-NA | 6099-0856 | V574-1 | CV1-CV4 | F1 | APQP | Assy | 2025-01-01 | 2024-08-28 |  | Finish | Finish | ASSY, IM, MM, PV-15-Aug | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-039 | HE020-32FU-LGR | 6099-0745 | V552-1 | CV1-CV4 | F1 | APQP | Unit | 2024-10-01 | 2024-08-05 |  | Finish | Finish | ASSY, IM, MM, PV, QA-20-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-040 | HE020-32FL-LGR | 6099-0746 | V553-1 | CV1-CV4 | F1 | APQP | Unit | 2024-10-01 | 2024-08-05 |  | Finish | Finish | ASSY, IM, MM, PV, QA-20-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-041 | HE020-32FL-B | 6099-0748 | V553-1 | CV1-CV4 | F1 | APQP | Unit | 2024-10-01 | 2024-08-05 |  | Finish | Finish | ASSY, IM, MM, PV, QA-20-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-042 | 12H28NYH30F-NA | 6099-0819 | V562-1 | CV1-CV4 | F1 | APQP | Assy | 2025-02-01 | 2024-08-05 |  | Finish | Finish | ASSY, IM, MM, PV, QA-20-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-043 | 12H28NYS30F-NA | 6099-0820 | V564-1 | CV1-CV4 | F1 | APQP | Child part | 2025-02-01 | 2024-08-05 |  | Finish | Finish | ASSY, IM, MM, PV, QA-20-Jul | Wait | NA | NA | Wait | Wait | Processing
C-APQP-045 | 12H24WYS42F-NA | 69109152 | V550-1 | CV1-CV2 | F1 | APQP | Child part | 2025-02-01 | 2024-07-02 |  | Finish | Finish | ASSY, IM, MM, PV-30-Jun | Wait | NA | NA | Wait | Wait | Processing
C-APQP-046 | 12H24WYO42F-GR | 69109151 | V551-1 | CV1-CV2 | F1 | APQP | Child part | 2025-02-01 | 2024-07-02 |  | Finish | Finish | ASSY, IM, MM, PV-30-Jun | Wait | NA | NA | Wait | Wait | Processing
C-APQP-047 | HFDU2-6F-HSG-NA | 6099-0433 | V536-1 | CV1-CV4 | F1 | APQP | Unit |  | 2027-01-05 |  | Finish | Finish | ASSY, IM, MM, PV, QA | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-048 | 12H26WYH08F-B | 6185-6097 | V587-1 | CV1-CV8 | F2 | APQP | Assy | 2024-09-27 | 2024-08-01 |  | Finish | Finish | ASSY, IM, MM, PC, PV, QA-29-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-049 | 12H26WYS08F-NA | 6189-6096 | V579-1 | CV1-CV8 | F2 | APQP | Child part | 2024-09-27 | 2024-08-01 |  | Finish | Finish | ASSY, IM, MM, PC, PV, QA-24-Jul | Wait | NA | NA | Wait | Wait | Processing
C-APQP-050 | 12H29NYL30F-B | 6099-0821 | V567-1 | CV1-CV4 | F1 | APQP | Unit | 2025-02-01 | 2024-08-05 |  | Finish | Finish | ASSY, IM, MM, PV-24-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-051 | 12H31NYH30F-GR | 6099-0823 | V562-1 | CV1-CV4 | F1 | APQP | Assy | 2025-02-01 | 2024-08-05 |  | Finish | Finish | ASSY, IM, MM-05-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-052 | 12H33NYH34F-NA | 6099-0825 | V561-1 | CV1-CV2 | F1 | APQP | Assy | 2025-02-01 | 2024-06-30 |  | Finish | Finish | ASSY, IM, MM-05-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-053 | 12H33NYS34F-NA | 6099-0826 | V563-1 | CV1-CV4 | F1 | APQP | Child part | 2025-02-01 | 2024-06-30 |  | Finish | Finish | ASSY, IM, MM, PV-24-Jul | Wait | NA | NA | Wait | Wait | Processing
C-APQP-054 | 12H34NYL34F-GR | 6099-0827 | V566-1 | CV1-CV2 | F1 | APQP | Unit | 2025-02-01 | 2024-08-05 |  | Finish | Finish | ASSY, IM, MM, PV-29-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-055 | 12H36NYH27F-NA | 6099-0829 | V560-1 | CV1-CV2 | F1 | APQP | Assy | 2025-02-01 | 2024-06-30 |  | Finish | Finish | ASSY, IM, MM-05-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-056 | 12H36NYS27F-NA | 6099-0830 | V563-1 | CV1-CV4 | F1 | APQP | Child part | 2025-02-01 | 2024-08-05 |  | Finish | Finish | ASSY, IM, MM-05-Jul | Wait | NA | NA | Wait | Wait | Processing
C-APQP-057 | 12H37NYL27F-B | 6099-0831 | V565-1 | CV1-CV2 | F1 | APQP | Unit | 2025-02-01 | 2024-08-05 |  | Finish | Finish | ASSY, IM, MM, PV-15-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-058 | 12H38N3H01F-NA | 6099-0795 | V559-1 | CV1-CV8 | F1 | APQP | Unit | 2025-02-01 | 2024-06-30 | 2024-07-01 | Finish | Finish | ASSY, IM, MM, QA-04-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-059 | 12H39N3H01F-NA | 6099-0799 | V559-1 | CV1-CV8 | F1 | APQP | Unit | 2025-02-01 | 2024-06-30 | 2024-07-01 | Finish | Finish | ASSY, IM, MM, QA-04-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-060 | 12H40N3H01F-NA | 6099-0803 | V559-1 | CV1-CV8 | F1 | APQP | Unit | 2025-02-01 | 2024-06-30 | 2024-07-01 | Finish | Finish | ASSY, IM, MM, PV, QA-05-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-061 | HFCV-H01M-NA | 6099-0757 | V545-1 | CV1-CV8 | F1 | APQP | Assy | 2024-10-01 | 2024-07-17 |  | Finish | Finish | ASSY, IM, MM, PV-18-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-062 | HFCV-S01-NA | 6099-0755 | V546-1 | CV1-CV16 | F1 | APQP | Child part | 2024-10-01 | 2024-06-05 | 2024-06-05 | Finish | Finish | ASSY, IM, MM, PV-05-Jul | Wait | NA | NA | Wait | Wait | Processing
C-APQP-063 | HFCV-H01F-NA | 6099-0754 | V547-1 | CV1-CV16 | F1 | APQP | Assy | 2024-10-01 | 2024-07-08 |  | Finish | Finish | ASSY, IM, MM, PV-18-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-064 | HFCV-H02F-NA | 6099-0759 | V548-1 | CV1-CV2 | F2 | APQP | Assy | 2024-09-01 | 2024-07-07 |  | Finish | Finish | ASSY, IM, MM, PC, PV-25-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-065 | HFCV-S02-NA | 6099-0760 | V548-1 | CV1-CV2 | F2 | APQP | Child part | 2024-09-01 | 2024-07-10 |  | Finish | Finish | ASSY, IM, MM, PC, PV-24-Jul | Wait | NA | NA | Wait | Wait | Processing
C-APQP-066 | H/LHSG6+2HYB-M | 6181-7654 | V576-1 | CV1-CV4 | F2 | APQP | Assy | 2024-09-27 | 2024-08-01 |  | Finish | Finish | ASSY, IM, MM, PC, PV, QA-26-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-067 | H/LRTN6+2HYB-M | 6181-7653 | V577-1 | CV1-CV8 | F2 | APQP | Child part | 2024-09-27 | 2024-08-01 |  | Finish | Finish | ASSY, IM, MM, PC, PV, QA-26-Jul | Wait | NA | NA | Wait | Wait | Processing
C-APQP-068 | 12C05WYH46F-B | 61855234 | V508-3 | CV5-CV6 | F1 | Add | Assy |  | 2024-06-24 | 2024-06-25 | Finish | Finish | ASSY, IM, MM, PV, QA-05-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-069 | 12E84WQH02F-B | 61855645 | V506-2 | CV5-CV12 | F2 | Add | Assy | 2024-07-08 | 2024-08-05 |  | MM-05-Jul | Finish | Wait-27-Jun | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-070 | 12790WQH06F-GR | 61854769 | V100-8 | CV41-CV56 | F2 | Add | Assy | 2024-07-22 | 2024-09-05 |  | MM-05-Jul | Finish | Wait-25-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-071 | 78190NYH63M-NA | 60989867 | V451-5 | CV11-CV14 | F1 | Add | Assy |  | 2024-09-05 |  | Finish | Finish | ASSY, IM, MM, PV, QA-10-Aug | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-072 | 12G02WYO42F-B | 69108617 | V473-2 | CV3-CV6 | F1 | Add | Child part |  | 2024-09-05 |  | Finish | Finish | ASSY, IM, MM, PV, QA-10-Aug | Wait | NA | NA | Wait | Wait | Processing
C-APQP-073 | LIF MP100GY-N | 60989028 | V394-2 | CV5-CV12 | F2 | Add | Assy | 2024-10-30 | 2024-10-15 |  | MM-01-Jul | Finish | Wait-01-Aug | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-074 | 12G02WYH42F-B | 61855876 | V471-3 | CV5-CV6 | F1 | Add | Assy |  | 2024-09-05 |  | Finish | Finish | ASSY, IM, MM, PV, QA-10-Aug | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-075 | 12520WQH08F-GR | 61851240 | V369-4 | CV13-CV20 | F2 | Add | Assy | 2024-10-18 | 2024-09-14 |  | MM-03-Jul | Finish | Wait-30-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-076 | 12E32NFH36F-NA | 60988853 | V475-3 | CV9-CV12 | F1 | Add | Assy |  | 2024-09-25 |  | Finish | Finish | ASSY, IM, MM, PV, QA-30-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-077 | CVR8282130600B | 69112828 | V330-3 | CV33-CV48 | F1 | Add | Unit |  | 2024-10-29 |  | Finish | Finish | ASSY, IM, MM, PV, QA-30-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-078 | 78190NYS63M-NA | 60989868 | V452-2 | CV5-CV6 | F1 | Add | Assy |  | 2023-12-19 | 2024-12-14 | Finish | Finish | ASSY, IM, MM, PV, QA-10-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-079 | 78240NYS63F-NA | 60989872 | V452-2 | CV5-CV6 | F1 | Add | Assy |  | 2023-12-19 | 2024-12-14 | Finish | Finish | ASSY, IM, MM, PV, QA-10-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-080 | 12F11NFH02M-NA | 6910-8306 | V517-1 | CV1-CV4 | F1 | Expand | Unit |  | 2024-06-26 | 2024-07-01 | Finish | Finish | ASSY, IM, MM, PV, QA-12-Aug | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-081 | 12F12NFH02M-B | 6910-8309 | V517-1 | CV1-CV4 | F1 | Expand | Unit |  | 2024-06-26 | 2024-07-01 | MM-08-Jul | PK-08-Jul | Wait-30-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-082 | 12F13NFH02M-L | 6910-8312 | V517-1 | CV1-CV4 | F1 | Expand | Unit |  | 2024-06-26 | 2024-07-01 | MM-08-Jul | PK-08-Jul | Wait-30-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-084 | FR25-32+6-11FN | 6920-3613 | V503-2 | CV3-CV4 | F1 | Add | Assy |  | 2024-05-17 | 2024-05-16 | Finish | Finish | ASSY, IM, MM, PV, QA-05-Jul | Wait-14-Jun | Wait-14-Jun | Wait-14-Jun | Wait-14-Jun | Wait-30-Jun | Processing
C-APQP-085 | HSG220+64FUB | 6099-0677 | V555-1 | CV1-CV4 | F1 | APQP | Unit |  | 2024-04-12 | 2024-03-25 | Finish | Finish | ASSY, IM-03-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-086 | HSG220+64FLB | 6099-0678 | V556-1 | CV1-CV4 | F1 | APQP | Unit |  | 2024-04-12 | 2024-03-25 | Finish | Finish | ASSY, IM, MM, PV-05-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-087 | HSG220+64FUNA | 6099-0679 | V555-1 | CV1-CV4 | F1 | APQP | Unit |  | 2024-04-12 | 2024-03-25 | Finish | Finish | ASSY, IM, MM, PV-05-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-088 | HSG220+64FUB2 | 6099-0681 | V555-1 | CV1-CV4 | F1 | APQP | Unit |  | 2024-04-12 | 2024-03-25 | Finish | Finish | ASSY, IM, MM, PV-05-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-089 | HSG220+64FLB2 | 6099-0682 | V556-1 | CV1-CV4 | F1 | APQP | Unit |  | 2024-04-12 | 2024-03-25 | Finish | Finish | ASSY, IM, MM, PV-05-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-090 | HSG220+64FUNA2 | 6099-0683 | V555-1 | CV1-CV4 | F1 | APQP | Unit |  | 2024-04-12 | 2024-03-25 | Finish | Finish | ASSY, IM, MM, PV-05-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-091 | HSG220+64FLNA | 6099-0680 | V556-1 | CV1-CV4 | F1 | APQP | Unit |  | 2024-04-12 | 2024-03-25 | Finish | Finish | ASSY, IM, MM, PV-05-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-092 | HSG220+64FLNA2 | 6099-0684 | V556-1 | CV1-CV4 | F1 | APQP | Unit |  | 2024-04-12 | 2024-03-25 | Finish | Finish | ASSY, IM, MM, PV-05-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-093 | 12808N6S02F-NA | 6098-6064 | V231-4 | CV25-CV40 | F1 | Add | Assy |  | 2024-02-28 | 2023-12-28 | Finish | Finish | ASSY, IM-05-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-094 | 12808N6H02F-B | 6098-6063 | V230-4 | CV33-CV48 | F1 | Add | Assy |  | 2024-02-28 | 2023-12-28 | Finish | Finish | ASSY, IM-01-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-095 | 12F38NFH08F-GR | 69108301 | V516-1 | CV1-CV4 | F1 | Expand | Unit |  | 2024-02-14 | 2024-02-14 | Finish | Finish | ASSY, IM, MM, PV, QA-30-Jul | Wait | NA | Wait | Wait | Wait | Processing
C-APQP-097 | 12H24WYH42F-B | 6185-6099 | V554-1 | CV1-CV2 | F1 | APQP | Assy | 2025-02-01 | 2024-07-24 |  | Finish | Finish | ASSY, IM, MM, PC, PV-30-Jul | Wait | Wait | Wait | Wait | Wait | Processing
C-APQP-098 | HFDS4-2F-HSG-B | 6099-0948 | V528-1 | CV1-CV16 | F1 | APQP | Unit | 2024-08-30 | 2023-09-28 | 2023-09-05 | MM, PC, PK-16-Jul | PC, PK, QA-16/Jul | Wait-17-Jul | Wait | NA | Wait | Wait | Wait | Processing